## Workshop Action Log
TSB Faster Payments Action Log
Action Id. | Action | Date Raised | Date Closed | Date Required | Owner | Status | Comments
1 | Recovery File Vs. FIM - What is the process for sending back a duplicate file eg a standing order file sent twice by mistake | 25/4/16 | 2016-10-05 | 2016-06-05 | Dave Godfrey | Closed | 10/5/16 - not an ACI requirement
2 | Define what USE CASES are needed to accept cases that wouild not be straight thru processing | 25/4/16 | 25/5/16 | 27/5/16 | TSB | Closed | 6/5/16 Response from TSB Personal Loans - Accept response Business Loans - Accept response CASS - Possible Accept Cards - QA Collection & Recoveries - Possible Accept Mortgages - Accept Payment Originated overseas - QA 9/5/16 Simon to provide level of detail ACI expects for this 10/5/16 TSB to provide the additional details discussed in workshop 12/5/16 target date 13/5/16 17/5/16 Date moved to 19/5/16 20/5/16 Meeting with ACI took place this week and date moved to 27/5/16 at request of TSB to confirm requirements 25/5/15 Information provided - Action Closed | CASS - Need to follow up to see if QA Collections and Recoveries - Need to follow up to see if QA CARDS - need a list of Sort codes and account numbers to be supplied
3 | Control Centre is replacing Platform Manager - when will this version be available and what documentation can be provided on the control centre | 25/4/16 |  | 31/7/16 | Jamie | Open | 12/5/16 3.3.1 is release and Target date is October - this date needs to be confirmed update to be provided 30/5/16 1/6/16 - Target Date is End November next update on this date to be provided end of July- Documentation to be available 10/6
4 | Is there a contract restriction on the number of end-points | 25/4/16 | 28/4/16 | 2016-06-05 | Gio | Closed | No Restriction is in place
5 | How do we connect to the isolation host? | 25/4/16 | 2016-03-05 | 2016-06-05 | Simon Harris | Closed | 3/5 UPF connects to the isolation host using TCP to port 4. The machine just has to have it’s firewall open on that port.
6 | Discussion needed to aid planning on deployment in UK vs Spain - Prod and Accept environments will be in UK all others will be in Spain | 25/4/16 | 17/5/16 | 2016-06-05 | Gio | Closed | 3/5 Added to agenda for workshops w/c 9/5 17/5/16 SIT in Spain, UAT in UK - Closed
7 | Provide BSIS with information on Software Delivery Process | 25/4/16 | 2016-12-05 | 2016-09-05 | Tracy | Closed | 9/5/16 Tracy to send details today 12/5/16 Closed
8 | What happens if accounting platform not available (ACI Store and Forward) - Can receiving interfaces deal with this? E.g. How can the accounting platform deal with receiving from SAF? | 26/4/16 | 2016-05-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS Implement Idempotence or a duplicate check in KC / AU. To be treated as a requirement for these interfaces.
9 | BSIS to look at how transactions appear on statements (as a result of failed payments and re-attempts) | 26/4/16 | 2016-12-05 | 2016-09-05 | TSB | Closed | 5/5/16 Response from BSIS For SO & Future Dated Payments a debit and a credit will be shown as AU does not support Hold. For other types (SIP/FDP) hold is possible and ACI will confirm or release the hold depending on the status from CI. 9/5/16 Miguel to follow up with Anil and provide response today 12/5/16 Closed no ACI Requirement
10 | Define how channels will deal with 15 second response - What can Proteo do | 26/4/16 | 2016-10-05 | 2016-09-05 | BSIS | Closed | 5/5/16 Response from BSIS The current thinking is that a WS interface into PROTEO will make the transactions synchronous. Therefore channels will wait for the timeout and if they timeout then channels will display an appropriate message. 9/5/16 BSIS has diagrams around this that need to be discussed later today with ACI 10/5/16 Closed
11 | Share List of Codes (ACI and CI) | 26/4/16 | 2016-09-05 | 2016-06-05 | BSIS | Closed | 3/5 – Information was requested regarding the response codes that were talked about in the workshops. The FPS Reference Guide is the place where this is documented from a product perspective. Until we define their endpoints we will not have all the values, but this doc will provide a starting point 5/5/16 Response from BSIS From out point of view, this actions should be in AC side. From Proteo Systems, we wil provide to the channels and to the rest of the TSB systems with the capability of error mapping. No requirement of this kind should be implemented by ACI. ACI will send scheme codes. 9/5/16 Action Closed
12 | API needed to determine if an FDP can be sent to fraud solution - | 26/4/16 |  | 26/5/16 | Carlos | Open | Anil 06/05/2016: Fraud business have confirmed that soft rejection of SIP must be notified to Fraud platform through the originating channel so that the event of rejection is included in customer profiling. Accordingly Fraud IT teams have initiated the discussions with Payments IT. Miguel / Carlos have to confirm that the discussions have happened and an agreement is reached for the API. 9/5/16 Work in Progress to finalise the interface - Date to be confirmed 12/5/16 Working assumption is that the channelwill provide the data that the Fraud system requires 17/5/16 on schedule 20/5/16 Plan provided by BSIS - BSIS expect a file from fraud 24/5 - completion date still to be advised 25/5/16 Details to be provided 26/5/16
13 | Will ACI receive a validated, well-formed outbound payment from intelligent channels or from dumb channels? Does ACI need to validate?. Where validation sits, needs discussion and decision | 26/4/16 | 2016-09-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS Validations sit in internal TSB service layers. ACI validations will work independently of channel validations. ACI will receive a well formed message.
14 | ACI to provide to BSIS a list of all documentation | 26/4/16 | 2016-06-05 | 2016-06-05 | Gio | Closed | 6/5/16 List provided by Gio Delivered already Hardware and Software Requirements UP Framework Product Overview Pre-installation guide Operations Guide FPS Gateway Reference Guide 1.3.2 FPS User Guide 1.3.1 Attached in mail 6/5/16 Release notes Systems Object Security Standard Security Best practices Platform Manager Guide Guidelines to PCI Compliance Configuration Builder Guide Installation Guide JMX Reference Guide
15 | BSIS to generate a unique (end to end) Payment Identification | 26/4/16 | 2016-05-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS Proteo will generate and internal id for every payment that will be share with ACI and the Scheme in every interaction. It will follow the Scheme rules for the Payment Id.
16 | BSIS to provide format of Party id, event type, unique payment identification | 26/4/16 |  | 26/5/16 | Carlos | Open | 5/5/16 Response from BSIS There is a work in progress with the fraud team in order to define the interface. 9/5/16 see Action 12
17 | BSIS to provide details of any additional data needed on the outbound SIP | 26/4/16 |  | 26/5/16 | Carlos | Open | 5/5/16 Response from BSIS Work in progress. Pending analys of all the teams involed (Fraud, Sanctions, …) 9/5/16 see Action 12
18 | Name and Address (e.g. related to #19, is the information needed if the sender keys it in) | 26/4/16 | 2016-05-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS Yes. This information will be providedby the channels or Proteo
19 | BSIS client needs to be built to fail if using SOAP endpoint | 26/4/16 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 9/5/16 Needs discussion later on integration 10/5/16 BSIS to address in design can be closed
20 | BSIS to revisit decision to use SOAP for endpoint to integration layer for SIP - MQ to be considered for integration layer endpoint | 26/4/16 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS We are going to use SOAP 9/5/16 Needs discussion later on integration 10/5/16 SOAP agreed to be used
21 | Can a series of different messages be defined for return to channel(Outbound SIP)? Yes a possibility, but is this a requirement | 26/4/16 | 2016-05-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS There is no requirement. It will be solved by PROTEO
22 | BSIS to confirm data and data format on accounting interface to IP (Part of Proteo) - What needs to be provided on a statement | 26/4/16 |  | 27/5/16 | BSIS/TSB | Open | 5/5/16 Response from BSIS We are defining a standard format for all the interactions among PROTEO Host and ACI. We will use this format in all the interactions (not for FRAUD and Sanctions) 9/5/16 Carlos and Andy to provide response end of the week 12/5/16 Andy to follow up and come back with a date 17/5/16 This work has been prioritised within BSIS, however it is not likely to complete by the end of this week - A date for completion will be provided 20/5/16 25/5/16 Details to be provided 27/5/16 1/6/16 - Plan presented to BSIS 31/5 to complete requirements gathering Phase - BSIS to confirm dates and approach
23 | BSIS to confirm data and data format on Interface from IP (Part of Proteo) | 26/4/16 | 2016-05-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS It is the same question and answer than above
24 | BSIS to provide response times from IP (Part of Proteo), agree a target for the build of Proteo IP component | 26/4/16 | 2016-10-05 | 2016-06-05 | ACI | Closed | 5/5/16 Response from BSIS We are not in the position of giving an answer to this. Proteo4UK is a new plattorm that is being built. Is this information really needed right now. Why? 9/5/16 Simon to provide details of the specifics that are required to complete the SDD 10/5/16 Value will be provided in SDD for BSIS sign-off
25 | How should UPF talk to IP (doesn’t exist today, to be built) in proteo check and book service? MQ? | 26/4/16 | 2016-09-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS It will be MQ. There will be a unique interface to IP that will be responsible of dealing with the Account System.
26 | ACI need to build a cycle check process (for settlement cycle) | 26/4/16 | 2016-10-05 | 2016-06-05 | Dave Godfrey | Closed | Part of Solution Scope Document
27 | BSIS require a cost estimate for exposing validation as a service | 26/4/16 | 2016-12-05 | 2016-12-05 | BSIS | Closed | 3/5 Date changed from 6/5 to 30/6 BSIS to follow up to see if still required 12/5/16 Validation wilbe done in the front end - Closed
28 | ACI to provide standard duplicate criteria for outbound SIP | 26/4/16 | 2016-04-05 | 2016-06-05 | Tracy | Closed | 4/5 Details provide in e-mail
29 | BSIS to provide details for duplicate checking on an outbound SIP | 26/4/16 | 27/5/16 | 20/5/2016 | BSIS/TSB | Closed | 9/5 Andy to confirm 10 /5 BSIS to follow up 12/5/16 Duplicate checking is a requirement of ACI - BSIS/TSB to provide the details of the requirement 17/5/16 On-schedule to provide on 20/5 internal meeting taking place today 20/5/16 Business has agreed requirements - Amol to provide requirements today 25/5/16 Action closed
30 | BSIS to confirm if Files need to be used for SOP interface - ACI recommendation is to not to use files | 26/4/16 | 2016-10-05 | 2016-06-05 | ACI | Closed | 5/5/16 Response from BSIS ACI will receive individual transactions in all cases. BSIS will handle debulking for bulk payments 9/5/16 ACI to consider the impacts of implementing files on cost and timelines then BSIS need to make a decsion 10/5/16 Decsion is to use files no impact analysis on cost and timescales needed
31 | Decision needed from excess management on HOLD account process (is Automatics used or not) | 26/4/16 | 2016-09-05 | 2016-06-05 | TSB | Closed | 6/5/16 Response from TSB Anil 05/05/2016: An agreement was made on 04/05/2016 that AU is the solution for SOP/FDP processing. 1. AU is the solution for processing SOP/FDP. 2. AU will be a black box from Faster Payments point of view. The response from AU for FPS will be Pay/No-Pay. 3. AU will do the 1st attempt and 2nd Attempt to pay SOP/FDP 4. Payments will attempt a 3rd retry on day 2 5. There is no risk prioritisation needed for SOP/FDP 6. SOPs processing deadline is 06:00 am (Majority, i.e. 90%+ of what is going to be sent that day to be sent between 0.01. and 06.00. At least 25% of the 90% must be sent by 03.00, 50% by 04.00 and 75% by 05.00) IT to further investigate and confirm 9/5/16 Processing is completed prior to ACI receiving the message so action closed - re-try process is different
32 | BSIS to provide details on the SMS interface (if ACI has to build the retry process)? | 26/4/16 | 2016-09-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS TBC - Not a requirement for SOP as it will be handled by AU. Not sure if we need it for anything else 9/5/16 Not a requirement for ACI
33 | Each FPS member is given strict session limits and TPS. Capacity discussion currently underway between Llyods and BSIS. Limits to be considered across both CI connections. Action BSIS to determine throttling requirements | 26/4/16 |  | TBA | Jamie | Open | 6/5/16 Response from TSB Yearly volumes and peak volumes are expected by close of play on Wednesday 9/5/16 Date changed from 6/5/16 to 11/5/16 12/5/16 - Target date is to receive on 13/5/16 17/5/16 - Kushan is summarising the data and will provide the detail and summary today 20/5/16 Information is with Carlos to review and provide to ACI 23/5 25/5/16 Carlos to send today - Information is based on peak data and is for Lloyds and assumption is that TSB is 18% of Lloyds 1/6/16 Details provided by BSIS on 25/5 - Jamie to provide sizing to TSB
34 | SOP - Is CASS check a requirement of ACI Solution (is Automatics used or not) | 27/4/16 | 2016-12-05 | 13/5/16 | Miguel | Closed | 5/5/16 Response from BSIS This has to be discussed internally with TSB Business Team to see how to proceed with this. This has to do with sending a letter to the client the first time a response from a payment has been received in with there has been a switch notification 9/5/16 CASS have confirmed that they are not doing this - BSIS need to dicide how to implement this and advise of requirement - action date changed from 6/5/16 to 13/5/16 12/5/16 CASS check is a requirement - Closed
35 | If CASS check is a ACI solution requirement - BSIS to provide interface format and how UPF should communicate For redirected accounts (CASS processing) response received from CI, does UPF need to call a service for SOP’s? | 27/4/16 |  | 24/5/16 | BSIS | Open | 5/5/16 Response from BSIS We need some clarification about this from ACI 9/5/16 - See action 34 12/5/16 - Update from Meeting today - BSIS to provide a date for a date 17/5/16 on schedule for Friday 20/5 with some risk to some of the interfaces 20/5/16 CASS requirements to be provided 24/5/16 24/5/16 Some of the requirements provided - ACI have highlightes what is missing based on the e-mail of 12/5 - Carlos to review what he believes has been provided - ACI to set up a call for 27/5/16 to review 1/6/16 - Plan presented to BSIS 31/5 to complete requirements gathering Phase - BSIS to confirm dates and approach
36 | Is CASS check needed for a SIP? Is CASS check needed for FDP | 27/4/16 | 2016-12-05 | 13/5/16 | Miguel | Closed | 6/5/16 Response from TSB Anil 05/05/2016: CASS check is needed for SIP and FDP. A communication is sent to the customer on first redirection and beneficiary details are updated 9/5/16 - See action 34 12/5/16 CASS check is a requirement - Closed
37 | Dave to send out photgraphs of flows discussed in workshops and decks used in workshops | 27/4/16 | 2016-05-05 | 2016-06-05 | Dave Godfrey | Closed | 4/5 Photographs issued - Slides to follow 5/5 Slides issued
38 | Batch FDP to be processed as per SOP and online FDP to be processed as a SIP - BSIS to confirm | 27/4/16 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS Confirmed 9/5/16 Automatics will be sending data now not data warehouse, data formats are needed - Date changed from 6/5/16 10/5/16 Automatics to be used
39 | Is automatics to be used? If automatics is used no accounting process is needed - BSIS to confirm requirement | 27/4/16 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS Yes - No accounting needed for SOPs & Future Dated Payments batch. Accounting is needed for FDP payments generated during the day. 10/5/16 Automatics to be used
40 | Interface to sanctions - BSIS to provide interface formats and how UPF should communicate | 27/4/16 |  | 24/5/16 | BSIS | Open | 6/5/16 Response from TSB Anil 06/05/2016: We have issued the draft interface specification issued to payments IT. Sanctions business have confirmed that the Sanctions IT and Payments IT have held discussions and the interface process is being established. All email communications between Sanctions IT and Payments IT have been forwarded to Miguel and Carlos. 9/5/16 - Date changed from 6/5/16 to 13/5/16 12/5/16 - BSIS to provide end of next week 17/5/16 on schedule for Friday 20/5 with some risk to some of the interfaces 20/5/16 Sanctions requirements to be provided 24/5/16 24/5/16 Some of the requirements provided - ACI have highlightes what is missing based on the e-mail of 12/5 - Carlos to review what he believes has been provided - ACI to set up a call for 27/5/16 to review 1/6/16 - Plan presented to BSIS 31/5 to complete requirements gathering Phase - BSIS to confirm dates and approach
41 | Confirm if exception management of payments held by sanctions needs to be automated or manual (e.g. return payment, unwind accounting) | 27/4/16 | 2016-09-05 | 2016-06-05 | TSB | Closed | 6/5/16 Response from TSB Anil 06/05/2016: Sanctions business have confirmed that payments held by sanctions will be processed manually. The initial response to the sanctions call will be automated. i.e. the response will be accept or hold. The subsequent responses to the hold scenario will be handled manually. 9/5/16 Closed
42 | Credit Transfer Session Plan - Acquirer Acceptance to be switched off - BSIS to confirm | 27/4/16 | 2016-09-05 | 2016-06-05 | TSB | Closed | 6/5/16 Response from TSB Anil 06/05/2016: Inward faster payments are mapped to a credit transfer session plan. From Inbound perspective Acquire acceptance is not required as the session plan is more required from outbound perspective. 9/5/16 Closed
43 | Credit Transfer Session Plan - Authorise Acceptance to be switched on with parameters repeat and initial checks switched on - TSB to confirm | 27/4/16 | 2016-09-05 | 2016-06-05 | TSB | Closed | 6/5/16 Response from TSB Anil: 06/05/2015: Inward faster payments are mapped to a credit transfer session plan. From Inbound perspective, authorise acceptance is required with repeat and initial checks switched on. 1. Repeat checks when initial is received first 2. Initial checks with repeat is received first 9/5/16 Closed
44 | Credit Transfer Session Plan - Risk Liability - ACI to document for TSB to review | 27/4/16 | 2016-10-05 | 2016-06-05 | Dave Godfrey | Closed | 10/5/16 To be documented in SDD
45 | Credit Transfer Session Plan - Authorise rules to be switched on - ACI to document for TSB to review | 27/4/16 | 2016-10-05 | 2016-06-05 | Dave Godfrey | Closed | 10/5/16 To be documented in SDD
46 | Credit Transfer Session Plan - Stand-in Authorise rules to be switched on - ACI to document for TSB to review | 27/4/16 | 2016-10-05 | 2016-06-05 | Dave Godfrey | Closed | 10/5/16 To be documented in SDD
47 | Credit Transfer Session Plan - Settlement to be switched on - ACI to document for TSB to review | 27/4/16 | 2016-10-05 | 2016-06-05 | Dave Godfrey | Closed | 10/5/16 To be documented in SDD
48 | Credit Transfer Session Plan - Notification to be switched on - ACI to document for TSB to review | 27/4/16 | 2016-10-05 | 2016-06-05 | Dave Godfrey | Closed | 10/5/16 To be documented in SDD
49 | ISO85/83 - ACI to confirm if this is EBCIDIC | 28/4/16 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 3/5 We can set the characters in MQ if we are using that. Alternatively if EBCDIC is required we can encode that in the Endpoint. – Please confirm requirement 10/5/16 agreed to close
50 | Meetings to take place next week to look at population of SDD (Participants Carlos/Amol/Stephen/Simon) | 28/4/16 |  | 27/5/16 | Tracy | Open | 3/5 Simon to issue SDD Questionairre 6/5 6/5 SDD Questionairre issued 10/5/15 Review to take place next week - Andy to set up meeting with Anil - Outstanding actions on SDD Questionairre Tab 17/5/16 - Meeting in place for 18/5/16 20/5/16 Tracy to reschedule Meeting to look at SDD questionaaire (further detailed meetings for setting up configuration will also need to be scheduled) 24/5/16 Meeting to be set up for w/c 6/6/16 - Meeting to cover remaining sections in the questionaaire yet to be answered and to review updates to sections where responses have been provided 1/6/16 Priority should be given to complete requirements - Meeting to be scheduled post 22/6 14/6/16 Meeting took place with BSIS on 9/6/16 and decision made to move forward with standard gateway and no orchestration - SDD started 13/6
51 | USM - BSIS to validate operations requirement for an alert based on SITL % | 27/4/16 | 28/4/16 | 2016-06-05 | TSB | Closed | Not a requirement
52 | ACI to provide information on Businesss Intelligence and confirm if this allows BSIS to view USM's | 27/4/16 |  | 2016-10-06 | Jamie | Open | 20/5/16 Jamie to provide an update on 25/5/16 25/5/16 Tracy to follow up with Jamie 1/6 Yes it does allow viewing of USM's - Documentation to be availabel 10/6
53 | SOP Initiation from Payment Warehouse?? Or elsewhere (Automatics)?? How will payments data be provided to UPF? | 27/4/16 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS Interface to be defined. SOP initiation for ACI will always be from Automatics 10/5/16 will be automatics
54 | How are FDP’s initiated Data Warehouse/Automatics, both? What are the accounting requirements? Is this depending on whether Batch or Online? Potentially two different process flows. | 27/4/16 | 2016-05-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS Data Warehouse and automatics for batch. Online FDPs from channels and accounting is in ACI
55 | Inbound SIP’s from CI Endpoint, IP proteo Timeout no response, Stand-in by UPF. How should SAF messages from QA process (Stand-in) be sent to IP proteo? Assumption - Using the same interface different MTI. | 27/4/16 | 2016-05-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS It’s a correct assumption. We will use a differen MQ queue but the format of the messages will be the same
56 | Req Ref 3.5.5.2.3 version 7.0 Detailed Design (Throttling for transactions to CI) - ACI to confirm repeat processing | 28/4/16 |  | 27/5/16 | Dave Godfrey | Open | 12/5/16 Details to be provided in SSD 20/5/16 No Update - Date moved from 20/5/16 to 27/5/16
57 | Req Ref 3.5.5.1.4 Veriosn 7.0 detailed design ACI to clarify how returns are matched | 28/4/16 |  | 27/5/16 | Dave Godfrey | Open | 12/5/16 Details to be provided in SSD 20/5/16 No Update - Date moved from 20/5/16 to 27/5/16
58 | For redirected accounts (CASS processing) response received from CI, does UPF need to call a service for SOP’s? | 28/4/16 | 2016-12-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS We need some clarification about this from ACI 10/5/16 See action 34 12/5/16 see action 35
59 | De-SAFing rate How do we manage the prioritization? | 28/4/16 |  | 27/5/16 | Carlos | Open | 9/5/16 - How much can be configured 12/5/16 Dave to respond next week 20/5/16 Response provided to BSIS - Carlos to review before action can be closed
60 | For USM or Admin Advice is Alert on Tivoli SNMP or Notification service to another endpoint? (restriction on 255 characters) | 28/4/16 |  | 26/5/16 | BSIS/TSB | Open | 5/5/16 Response from BSIS Not yet closed. There will be a Technical Notification System basic on SNMP and a Business Case Management 9/5/16 BSIS and TSB decisions needed (Microsoft Dynamics) unlikely to resolve this action this week - business realtime/ops some realtime - New date to be provided 11/5/16 17/5/16 on schedule for Friday 20/5 with some risk to some of the interfaces 20/5/16 No Date provided for completion of the requirements - Next step is an internal BSIS meeting on 23/5/16 25/5/15 Details to be provided 26/5/16 1/6/16 - Plan presented to BSIS 31/5 to complete requirements gathering Phase - BSIS to confirm dates and approach
61 | Req Ref 3.5.5.1.4 Reversals - BSIS to understand how the accounting works and what the impacts are to customer statements (decision has no impact to ACI solution) | 28/4/16 | 2016-09-05 | 2016-06-05 | TSB | Closed | 6/5/16 Response from TSB Anil 05/05/2016 Proposed two options to IT. From Business perspective, the decision is not to have any impact on customer statements and customer experience. Therefore, in the above scenario, there are two possible scenarios that we can suggest. Scenario 1: When a reversal is received and the original is applied to the account, then the reversal is shown in the customer statement. Scenario 2: When a reversal is received and the original is NOT applied to the account, then the suggestion is to auto reconcile the entries without impacting the customer statement. 9/5/16 Closed
62 | BSIS to provide list of codes for soft and hard reject | 28/4/16 | 2016-10-05 | 2016-09-05 | BSIS | Closed | 5/5/16 Response from BSIS Supplied 9/5/16 AMOL to send 9/5/16 RespCde QualCde Payment Type Description 9 913 SOP Duplicate FPID 9 942 SOP Net sender cap breach 1 901 All CI Unavailable 1 902 All Timeout to CI 1 1909 All System malfunction The origin of these codes is in LBG. As we are mandated to recreate the As-Is, it makes sense to reuse them. Also 9912 & 9911 (mentioned in Citibank scenario whitepaper) are not used currently by LBG, but we should use them as well. There is some debate generally about whether all these codes actually constitute as soft reject codes (913 & 942 have never been received by LBG), but my feeling is that to round off all the scenarios we should still use them.
63 | BSIS to provide white paper (2012 Citibank) | 28/4/16 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS - In progress 9/5/16 Received from AMOL
64 | Req Ref 3.5.5.2.3 version 7 design Document BSIS to confirm message to customer | 28/4/16 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS - We need some clarification about this from ACI 10/5/16 no recollection of action agreed to close
65 | Ensure Training Requirements are covered | 28/4/16 | 17/5/16 | 2016-06-05 | BSIS/ACI | Closed | To be included in workshop or further meeting to be set up - E-learning currently out of scope 6/5 on Agenda for workshops w/c 9/5 17/5/16 Offerings provided in Workshops - closed
66 | Tuesday and Thursday follow up meetings to be set up w/c 2 May | 28/4/16 | 29/5/16 | 2016-06-05 | Gio | Closed | 3/5 Meetings in Calendar - action closed
67 | Provide a copy of plan and testing Strategy | 2016-03-05 |  | TBA | BSIS | Open | 17/5/16 High Level plan presented on 12/5/16 - Next step is to add more detail plaanning meeting scheduled for w/c 23/5 14/6/16 Detail plan and test strategy still to be provided
68 | A solution Scope Document will be completed to cover both the standard gateway and the orchestration - this is a high level document outlining the scope that will need to be signed off by BSIS – this will allow us to give indicative milestones in order to aid BSIS high level planning. Tracy to see if a sample document can be provided to aid understanding | 2016-03-05 | 2016-05-05 | 2016-06-05 | BSIS | Closed | 5/5 Sample Document provided by Tracy
69 | All actions were set up with an initial date of 6/5 – All to notify Tracy of any amendments to dates | 2016-03-05 | 2016-09-05 | 2016-06-05 | All | Closed
70 | BSIS informed that no modulus checks need to be done by ACI but that the modulus checking service may need to be called – BSIS to confirm | 2016-03-05 | 2016-10-05 | 2016-06-05 | BSIS | Closed | 5/5/16 Response from BSIS I think this is a bad idea. ACI services should not be reused. 9/5/16 Still under discussion - need date to be provided by BSIS 10/5/16 No requirement for ACI
71 | BSIS requested information from ACI on standard customer support (SLA’s) vs. premium customer support (SLA’s) – Action Gio to provide update 6/5 | 2016-03-05 | 2016-12-05 | 2016-06-05 | Gio | Closed | 4/5 Slides provided by Gio - walkthru to take place w/c 9/5 12/5/16 Closed | on agenda for THurs
72 | BSIS asked if they could have information on a typical infrastructure prior to the workshops next week – ACI to see what can be provided. | 2016-03-05 | 2016-10-05 | 2016-04-05 | Simon Harris | Closed | 4/5 Response provided 10/5 Typical infrastructure and recommendation discussed - agreed to close
73 | Discuss de-saffing Straegy for Migration | 2016-09-05 | 2016-12-05 | 2016-12-05 | Dave Godfrey | Closed | 12/5/16 discussed in workshops
74 | Preferred Stack is Linux (Redhat) –HAR-MCAS, BSIS use Red hat. Oracle is DB option. Do BSIS use Oracle? What will BSIS use? What target versions for Linux Redhat and Oracle, if used for this project? | 2016-09-05 | 2016-10-05 | 13/5/2016 | BSIS | Closed | 10/5/16 - Redhat Enterprise Linux, Intel x86_64
75 | Any recommendations on the number of Network cards per Server? Action ACI | 2016-09-05 |  | 27/5/16 | Simon | Open | 12/5/16 A minimum of 2 is required
76 | ACI to check when Oracle 12c will be certified | 2016-09-05 | 2016-10-05 | 13/5/2016 | Simon | Closed | 10/5/16 Certified in 3.2.2 current version
77 | Need to understand BSIS Plans for Oracle 12c and Red hat 7 | 2016-09-05 |  | 27/5/16 | BSIS | Open | 10/5/16 Confirmed will use Oracle 12c 12/5/16 Redhat still to be confirmed
78 | IBM are going to host for BSIS - Carlos to chek if it will be on ibm hardware | 2016-09-05 | 2016-10-05 | 13/5/2016 | Carlos | Closed | 10/5/16 - Redhat Enterprise Linux, Intel x86_64
79 | BSIS to send infrastructure diagrams | 2016-10-05 |  | 25/5/16 | Carlos | Open | 12/5/16 diagrams have been updated to be sent today 17/5/16 Version 3 provided - USM diagram to be provided 20/5/16 20/5/16 No date available to complete this action - next step is BSIS internal meeting planned for 23/5/16 25/5/16 New versions to be sent today - naming conventions to be aligned to 'plan' spreadhseet 1/6 Version 5 sent 26/5 does not include fraud
80 | Need to know if Advanced security will be used for Oracle Database (impacts sizing) | 2016-10-05 |  | 27/5/16 | Carlos | Closed | 12/5/16 Needed for SDD 1/6/16 Advance Security is required
81 | Need to understand from BSIS version of MQ being used ( 7.1?) | 2016-10-05 |  | 27/5/16 | Carlos | Open
82 | What is maximum inbound TPS that BSIS require - for hardware sizing Gateway to Proteo | 2016-10-05 |  | 13/5/2016 | BSIS | Open | 10/5/16 refer to previous action 33
83 | What is maximum outbound TPS that BSIS require - For Hardware sizing Proteo to Gateway | 2016-10-05 |  | 13/5/2016 | BSIS | Open | 10/5/16 refer to previous action 33
84 | Need the throttling limits - for Hardware sizing - Gateway to CI | 2016-10-05 |  | 13/5/2016 | BSIS | Open | 12/5/16 Scheme needs to provide this information 17/5/16 Andy and Carlos to discuss - Update to be provided 20/5 20/5/16 Update to be provided next week - Extrapolation assumption should be that 18% of Lloyds traffic is for TSB
85 | 6.1 Risk Parameters for Host (Outbound Payments) Queries: 1. Are different alerts possible at different levels? E.g. When TSB is reaching 50% of Participant NSC, Participant NST, CI NSC, CI NST – raise an alert to the team for notification purposes And Notification alerts for 50% + up by 10% every time. And an action alert when the above reaches 80%. 2. How do other banks generally use this alerting mechanism for this rule. | 2016-10-05 | 2016-10-05 | 13/5/2016 | ACI | Closed | 10/5/16 Dave explained in workshops - agreed to close
86 | SOAP standards/versions to be provided by BSIS. | 2016-10-05 | 2016-12-05 | 13/5/2016 | BSIS | Closed | 12/5/16 not required
87 | Who purges the data from the Offload DB | 2016-10-05 |  | 27/5/16 | BSIS | Open | 12/5/16 Need to confirm if there are any tools 20/5/16 Response provided by ACI - BSIS to review to confirm closure
88 | Files need to be used for SOP interface - Will there only be one File or Multiple Files? When will File format be defined/provided? What do we do if there are invalid entries in a File? | 2016-10-05 |  | 26/5/16 | BSIS | Open | 17/5/16 on schedule for Friday 20/5 with some risk to some of the interfaces 20/5/16 Multiple Files will be used - Interface and Flow details to be provided 25/5/16 25/5/16 Details to be provided 26/5/16 1/6/16 - Plan presented to BSIS 31/5 to complete requirements gathering Phase - BSIS to confirm dates and approach
89 | Gio to send PCS details to BSIS outlining what options can be picked | 2016-11-05 | 20/5/16 | 13/5/16 | Gio | Closed | 17/5/16 Due to leave of PCS teammanagement this information will be provided 18/5/16 20/5/16 Information provided by Gio
90 | Could the report writer point to an additional offload database | 2016-11-05 |  | 27/5/16 | Jamie | Open
91 | Clarify if standard reports are delivered as part of BI | 2016-11-05 |  | 20/5/16 | Jamie | Open | 17/5/16 awaiting response from Product team 20/5/16 Jamie to provide an update 24/5/16 25/5/16 Tracy to follow up with Jamie 1/6/16 No standard reports delivered as part of BI
92 | Drop dead dates for all requirements | 2016-11-05 |  | TBA | Tracy | Open | 12/5/16 Actions highlightes in red on this list - Will raise any additional items 17/5/16 Request from Andy to advise on any impacts to plan 20/5/16 impacts to plan to be provided as soon as requirement dates are confirmed - at this point there will be a delay to the orchestration proposal based on the requirement dates provided 1/6/16 - Plan presented to BSIS 31/5 to complete requirements gathering Phase - BSIS to confirm dates and approach
93 | Provide report requirements (list of reports) | 2016-11-05 | 17/5/16 | 13/5/16 | Andy | Closed | 17/5/16 Closed
94 | Can reports be scheduled | 2016-11-05 |  | 27/516 | Dave Godfrey | Open | 1/6/16 Reports cannot be sheduled
95 | For Hardware Sizing - BSIS to provide Hardware refresh policy | 2016-12-05 | 20/5/16 | 20/5/16 | BSIS | Closed | 17/5/16 Carlos to provide 20/5 20/5/16 BSIS advised a 5 year policy - Closed
96 | Provide QA (SAFing) for Hardware sizing | 2016-12-05 |  | 27/5/16 | BSIS | Open | 17/5/16 Date changed from 13/5/16 to 27/5/16 25/5/16 Carlos to speak to Amol and then raise with ACI if action is not clear
97 | BSIS to provide requirements for Training (Courses Required, No. of People per course per functional area, When Required, Location of Courses) | 2016-12-05 |  | 2016-03-06 | BSIS | Open | 17/5/16 Update to be provided on next call 20/5 20/5/16 Date changed from 20/5/16 to 3/6/16
98 | BSIS to review Governance model and provide feedback | 2016-12-05 |  | 27/5/16 | BSIS | Open | 17/5/16 Andy and Carlos to review and provide feedback 20/5/16 Date moved from 20/5 to 27/5 1/6 Governance model provided 31/5
99 | BSIS to provide test support Requirements/Implementation Support Requirements | 2016-12-05 |  | 30/5/16 | BSIS | Open | 12/5 this can only be done once testing strategy and plan is in place
100 | BSIS to provide dates for first steering committee meeting (aim is to have first one after indicative planning) w/c 30/5? | 2016-12-05 |  | 27/5/16 | BSIS | Open | 17/5/16 will be done once action 98 complete 20/5/15 Date moved to 27/5/16
101 | Planning Meeting to take Place w/c 23/5 - Tracy to set up Meeting 12th December start of Functional Testing TSB/BSIS to consider Deployment Strategy Environment Readiness Test Strategy Training for testers and people maintianing testing systems Interface readiness ACI to consider how a phased deployment may work Key Planning points Scheme Certification - everything needs to be in place starts 12/12/16, SIT in Spain UAT in UK Self cert and cert in UK Assumption is that Performance and Volume needs to be done for certification Friends and Family start date is immovable as part of whole programme (this is driver) | 2016-12-05 |  | 27/5/16 | BSIS/TSB/ACI | Open | 17/5 Meeting set up
102 | Kushan to send slides of Plan | 2016-12-05 | 20/5/16 | 13/5/16 | TSB | Closed | 17/5 Slides to be sent today 20/5/16 Closed
103 | Provide Slides for Training, IM Methodolgy and Deliverables | 2016-12-05 | 17/5/16 | 13/5/16 | Tracy | Closed | 17/5/16 Closed
104 | Communications questions after ACI workshop Sant Cugat 1/ What is the maximum latency that for Data Center Interconnection links does the 2-stack ACI architecture support? We are considering one stack per DC and the link interconnecting both has a latency. We have to make sure it is below the maximum accepted by ACI for 2 stacks. 2/ For the proposed ACI architecture, there is a number of servers. We need to know how many network cards/ports per server are requested. Also, if they are 10G or 1G. 3/ What TCP port needs to be in listening mode in the “isolation host”? 4/ List of TCP/UDP ports between Offload DB, DB, MCAS and HARs in the same stack and in between stacks and with the CI. 5/ Explain the use of Load Balancer between MCAS and HARs for Web Services (i.e. design guide, reasons and benefits, pros and cons to use it, why only for Web Services and not for MQ,…) 6/ Although not recommended, please, provide some documentation on the use of a Load Balancer between CI and HAR (for CI disaster recovery) 7/ Confirm ACI can be configured so that connections go through the same HAR they were started from (pros and cons) 8/ Please confirm if for outbound connections to the CI the response from CI would only go through the same HAR that initiated the connection. | 17/5/16 |  | 27/5/16 | Carlos | Open | 1 We require less than 10ms between the servers that house the UPF platform. In fact, the lower the better. Please note, this must be a consistent low latency as the system components are self-monitoring and unpredictable spikes and periods of higher latency between UPF and the databases will adversely impact system performance and may cause the system to take its own remedial action. 2 We are going to have to check with the product team on the question of the number of cards. My expectation is that the network cards should be as fast as possible, but it depends on your own internal LAN/ WAN latency as to whether this is justified. 3 The MCAS platform requires a connection to a server on TCP port 4. This port needs to be open and available to the MCAS server at all times. This server is not an ACI supplied server, just a 100% available server within the data centre that has this port open. 4 We cannot supply all of this information in detail yet as is will be determined by the overall design of the platform. For instances, the CI ports will need to be determined between TSB and FPSL based on the number of servers and the required payment types that are going to be supported. This information will need to be agreed over the course of the project and will be documented in the Solution Detail Document for the gateway. However, the ACI document ‘UPF 3.2.2 - Pre-Installation Guide.pdf’ does give general port information that is required for UPF implementation and gives recommendations on firewall settings, etc. 5 ACI does not recommend or require a load balancer to run the UPF and therefore we cannot suggest the pros and cons from a UPF perspective as it is outside of our product scope. However, the key benefit as we see it is on the client side (i.e. proteo) as it will not have to manage the multiple connections required into the UPF. If you using a two stack deployment as we have stated, you will have two ICE-xs processes to communicate with for incoming WS messages 6 Unfortunately we do not have any documentation on this. As was mentioned in the workshop we understand some customers have used products such as F5, but this was outside of the scope of the ACI project and therefore not something we were directly involved with. We may need to engage with you directly to have discussions on this and the previous question when we come to system design. 7 The UPF will ensure that responses to the CI go back down the same socket as the request, if it is available. The UPF can be configured to attempt to respond to the same system, using another available connection in the case that the original is no longer available. However, this often has implications for the sending system and this is not always recommended or possible. TSB/BSIS will need to agree this behaviour with Vocalink. 8 The CI rules state that the response for an outbound payment will be returned on the same session. For us that means the established socket with the CI and therefore the same HAR / ICE-xs process that sent the request. 25/5/16 Carlos to review and confirm if can be closed
105 | Please find attached a document (Infra MD03-D0454- TSB-MID-PAY-ACI-VL v1.1) which covers the proposed infrastructure for the different environments prepared by our Infrastructure Team. This documents will change based on the sizing of the platform in production, but should be considered final for the Development and Integration environments that are going to be located in Spain. Could you please double check and confirm that it is aligned with what discussed during the workshops? We want to launch the procurement procedure for the environments in Spain ASAP. Besides that document, you can see attached the Technical Requirements for the Databases that we need to create for the ACI product. We should provide that information to the infrastructure team for the databases to be created. Our concern is to advance this information too for the environments in Spain. Additionally, we have a few questions that we would need to be answered. Questions related to Section 3: UPF sub components (UPF 3.2.2 - Hardware & Software Requirements document) I. Regarding the requirements about these modules, are the following subcomponents including only in MCAS server or in both servers (MCAS and HAR)? We will configure a 3-tier deployment architecture (HAR server, MCAS server and DB server). • APSF v1.4 Entitlement Framework • PIM v1.4 • ICE-XS v5.5.151123 II. APSF v1.4 Entitlement Framework is an optional module for the current release 3.2.2 , but it will be bundled in 3.3 release. Which version of UP Framework will be installed? Are we going to install and configure this module for Faster Payments in BS? III. Does HAR server require the installation of Java and JDK? IV. ICE-XS v5.5.151123 requires Websphere MQ 7.5 for Linux systems therefore we understand that this MQ software will be installed in MCAS server, but MQ 8.0 version is supported and could it be installed? V. APSF v1.4 Entitlement Framework and ICE-XS v5.5.151123 modules require a set of Third Party Libraries (Apache, Xalam, etc.). This set of libraries are including as part of any release or we would need to install them on each server? (We have assumed in the attached document that these libraries will be installed in MCAS server excepting APSF (Java SDK and UI)). | 18/5/16 |  | 27/5/16 | Tracy | Open | 25/5/16 Tracy to provide a date on whenthis can be reviewed 1/6 Feedback to be provided by the end of this week 14/6 Feedback provided 7 June - Further questions raised 13 June
106 | Carlos to provide BSIS plan so that ACI can understand any expectations of them - For Example Review of Infrastructure Documentation | 20/5/16 |  | 30/5/16 | Carlos | Open | 25/5/16 - Date moved from 27/5/16 to 30/5/16
107 | From Planning meeting on 31/5 Tracy to provide templates of deliverables | 31/5/16 |  | 31/5/16 | Tracy | Open | 1/6 Templates provided
108 | From Planning meeting on 31/5 Tracy to provide order of deliverables for plan and design phase (order for solution Planning is in the attached plan) | 31/5/16 |  | 31/5/16 | Tracy | Open | 1/6/16 Details provided 31/5
109 | From Planning meeting on 31/5 Tracy to provide details of potential drop content – this will need to be aligned to BSIS plans | 31/5/16 |  | 31/5/16 | Tracy | Open | 1/6/16 Details provided 31/5
110 | From Planning meeting on 31/5 BSIS to consider plans and provide feedback – Meeting to be set up by Miguel for this week | 31/5/16 |  | 2016-03-06 | Miguel | Open | 14/6 Planning meeting took place on 9/6 and following decisions made 1) BSIS have no time to move forward and provide the additional requirements for orchestration 2) BSIS will undertake orchestration
111 | From Planning meeting on 31/5 BSIS to consider what is necessary to carry out certification testing (critical path activities) | 31/5/16 |  | 2016-03-06 | BSIS | Open | 14/6 Planning meeting took place on 9 June and no functionality could be de-scoped for certification
112 | From Planning meeting on 31/5 ACI to help BSIS understand any areas of improvement in plan (pinch points on scope) | 31/5/16 |  | 2016-01-06 | Tracy/Jamie | Open | 1/6/16 Left VM with Andy to call back 14/6 Planning meeting took place 9 June to share plans and areas of improvement
113 | ACI to provide details of gaps in BSIS plan | 31/5/16 |  | 2016-03-06 | Tracy | Open
114 | From Planning meeting on 31/5 ACI to send copy of indicative plan and plan for a plan | 31/5/16 |  | 31/5/16 | Tracy | Open | 1/6/16 Plans sent 31/5/16
115 | Tracy to provide feedback on the requirements provided by Nury on 26/5 | 26/5/16 |  | 31/5/16 | BSIS | Open | 1/6/16 Feedback provided 31/5 14/6/16 BSIS to review feedback
116 | Andy to provide Scheme Testing dates | 26/5/16 |  | 26/5/16 | Andy | Closed | 1/6 Details provided 26/5 - Functional Cert 13/12/16-23/01/17 - Non Functional Cert 14/2/17-8/3/17
117 | From Anil Is there any functionality on gateway product, that a customer limit can be checked? Meaning – The scheme limit to send and receive faster payments is £250,000. Bank Limit (e.g.) is £100,000 Of which, Mobile is (e.g) £10,000 Branch is (e.g.) £10,000 Internet Banking is (e.g.) 25,000.. etc If a particular customer can initiate the payment through all these sources, and cumulative of such transactions is more that £100,000, do you think we can configure a rule to reject payments over and above such cumulative limit? | 31/5/16 |  | TBA | Simon | Open | 14/6/16 response provided on 7 June 'This is not something that is current in the gateway'
118 | From Planning meeting on 31/5 Miguel to advise how long BSIS need to review and sign-off Solution Scope Document | 31/5/16 |  | TBA | Miguel | Open
119 | From Planning Meeting 9 June 16 ACI to confirm delivery date for completion of Solution Detail Document for standard gateway | 2016-09-06 |  | TBA | Tracy | Open
120 | From Planning Meeting 9 June 16 ACI to confirm project plan for delivery of ‘Standard Gateway’ | 2016-09-06 |  | TBA | Tracy | Open
121 | From Planning Meeting 9 June 16 BSIS to confirm Host/CI formats ISO20022 or ISO5853 | 2016-09-06 |  | TBA | BSIS | Open
122 | From Planning Meeting 9 June 16 ACI to send full set of 3.3 product Manuals | 2016-09-06 |  | 2016-10-06 | Tracy | Open | 10/6 Sent list of documentation to BSIS for them to identify any missing items 13/6 Sent 2 missing documents - action can be closed
123 | From Planning Meeting 9 June 16 ACI to provide details of ‘how to approach orchestration’ – what documents to use for guidance | 2016-09-06 |  | TBA | Jamie | Open
124 | From Planning Meeting 9 June 16 BSIS to look at standard gateway formats with an aim to discuss questions with ACI 20/6 | 2016-09-06 |  | 17/6/16 | BSIS | Open
125 | From Planning Meeting 9 June 16 ACI to look at the easiest way to deliver orchestration for re-consideration | 2016-09-06 |  | TBA | Jamie | Open
126 | From Planning Meeting 9 June 16 Product Upgrade to 3.3.1 for ICE-XS and BI Packs – Current expected availability date November 2016 BSIS require a proposal from ACI on how best to upgrade and when | 2016-09-06 |  | TBA | Jamie | Open
127 | From Planning Meeting 9 June 16 BSIS to include upgrade to 3.3.1 in current plans | 2016-09-06 |  | TBA | BSIS | Open
128 | From Planning Meeting 9 June 16 Product Upgrade to 3.3.1 for ICE-XS and BI Packs – Current expected availability date November 2016 ACI to confirm if/when HAR will be sunset ACI to confirm if upgrade will have any impact ACI to confirm if ICE-XS and HAR need to be on different boxes | 2016-09-06 |  | TBA | Jamie | Open
129 | From Planning Meeting 9 June 16 Concern expressed over terminology in documents that require sign-off by BSIS ACI to ensure terminology is defined in a glossary/explained in a walkthru | 2016-09-06 |  | 2016-10-06 | Tracy | Open | 14/6/16 Team advised
Decisions
D1 | Consistent Message format for all channels from the integration layer to ACI - make as assumption | 26/4/16
D2 | ACI will validate the format and context of the data and will check for duplicates (on requests) | 26/4/16
D3 | Validation is not exposed in standard solution | 26/4/16
D4 | Interface to IP does not currently exist | 26/4/16
D5 | Interface Endpoint to/from IP is MQ - Fixed Format | 26/4/16
D6 | Solution Detail Design covers standard gateway configuration (excludes orchestration) - subject to further feedback from ACI | 25/4/16
D7 | Credit Transfer Session Plan - Risk liability check to be switched on for outbound only | 27/4/16
D8 | No Modulus checks need to be performed by ACI | 2016-03-05
Assumptions
A1 | SIP Request Data contains Debtor A/c number and Sort Code, Creditor A/C number and Sort Code, Amount, Reference, PAYM details and BSIS Specific data Party-id, Channel id, Event Type, Timestamp | 26/4/16
A2 | Interface to IP (Part or Proteo) data contains Credit Account number and Credit Amount, Debit Account Number and Debit Amount, Posting Ref and Timestamp | 26/4/16
A3 | Interface From IP accounting (Part or Proteo) data contains Decision yes or no and Reason Code, | 26/4/16
A4 | we use the same Endpoint to communicate with IP in proteo for accounting for SOP as with SIP | 26/4/16
A5 | FDP's work as per SOP except that there is no retry process | 27/4/16
A6 | Acquiring Acceptance rules (Decision table) in UPF will not be utilized as checking/validation will be done by TSB in the Channels prior to payment initiation to the UPF Endpoint(s). | 27/4/16
A7 | Authorizing Acceptance rules (Decision table) in UPF. Institution Availability check will not be utilized as continue sending to CI to manage where TSB is the Acquirer. | 27/4/16
A8 | Authorizing Acceptance rules (Decision table) in UPF. Message Repeat Request and original checks will be used where TSB is the Authorizer. | 27/4/16
A9 | Acquiring Acceptance rules (Decision table) in UPF will not be utilized for inbound. | 28/4/16
A10 | Authorizing Acceptance rules (Decision table) in UPF. Expected only Repeat check and Original check will be utilized for inbound. | 28/4/16
A11 | Risk Liability Checks will not be utilized for inbound. | 28/4/16
A12 | All FDP's to be sent to Fraud regardless of whether inside/outside the 15 minute tolerance | 26/4/16
A13 | Financial Crime out of Scope - Sanctions is in scope | 26/4/16
A14 | There is a two stage accounting process - earmark funds first and then debit for outbound SIP | 26/4/16

## Sheet1
TSB Faster Payments Action Log
Action Id. | Action | Date Raised | Date Closed | Date Required | Owner | internal/ External | Status | Comments | Estimate impact
1 | Get Agreement from BSIS one call to Proteo (merge of resgister and accounting endpoint) for inbound | 28/6/16 |  |  | BSIS | E | Open |  | L
2 | BSIS to confirm ISO8583 with a variable bitmap for all endpoints | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6. However sanctions is NOT ISO8583 | L
3 | BSIS to confirm flow required for Payment overseas and associated exception conditions (including sanctions dialogue and protocol) | 28/6/16 |  |  | BSIS | E | Open | Protocol is confirmed as WS | XL
4 | BSIS to confirm that they will create the return on a declined advice | 28/6/16 |  |  | BSIS | E | Open |  | L
5 | BSIS Confirmed no Fraud for incoming/outgoing - This will be done via proteo | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | XL
6 | Offload database not going to be used for settlement but will be for reconcilation | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | n/a
7 | Additional data needs to be in the ISO8583 - ACI to agree what field needs to be used (suggestion Field 48) | 28/6/16 |  |  | ACI | E | Open | Confirmed the need in w/shop 29/6. Exact details defined in future workshops | M
8 | BSIS to confirm that they will do the accounting hold processing from the channel(outbound) | 2016-06-28 |  |  | BSIS | E | Open |  | M
9 | No reversals to be generated to Proteo by the gateway | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | n/a
10 | Eight hours of SAF capacity required for peak processing - ACI to include in future sizing | 28/6/16 | 2016-06-29 |  | ACI | E | Closed | BSIS agreed in w/shop 29/6 | n/a
11 | BSIS require internal priority for live payments over SAF - ACI to advise how system processes SAF queue to be configured for advices and requests separate to each other | 28/6/16 |  |  | ACI | E | Open |  | n/a
12 | Network Management - Proteo host network dialogue - BSIS to look at what they will put in place - ACI recommendation is to do this post certification | 28/6/16 |  |  | ACI | E | Open | ACI to provide information on NMM implementation. BSIS agree its not certification requirement. Changed owner to ACI | S
13 | Inbound payments - BSIS to provide response code mapping | 28/6/16 |  |  | BSIS | E | Open |  | n/a
14 | BSIS to provide update list of soft rejects | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | Email provided previously. Only difference is CI down. Only relevant on the SIP to FDP conversion | n/a
15 | No requirement for Outbound admin Messages other than those from the standard gateway | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | n/a
16 | ACI to include an example of a corrupt message flow from the CI | 28/6/16 | 2016-06-29 |  | ACI | E | Closed | To be published in next release of msg flow document | n/a
17 | Cycle check by the gateway is not a requirement of ACI and will be handled by Proteo | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | M
18 | Proteo will manage CASS msg flow | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | L
19 | BSIS to provide functional certification tests | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | n/a | x
20 | BSIS to provide updated functional diagram | 28/6/16 |  |  | BSIS | E | Open |  | n/a
21 | USM messages - Future requirement post friends and family to look at sending to a case management tool | 28/6/16 |  |  | BSIS | E | Open |  | n/a
22 | USM messages - BSIS to send a list of messages and destinations (Tivoli or Proteo) | 28/6/16 |  |  | BSIS | E | Open |  | n/a
23 | 1.4.3 - Timeout on CI on outbound payment - BSIS to confirm flow - Potential number of action codes to be returned to channels 2 options SAF immediately/realtime then SAF - what is message to channel | 28/6/16 |  |  | BSIS | E | Open |  | L
24 | To check in the event of consecutive outbound timeouts to the CI do we log off | 28/6/16 |  |  | ACI | I | Open |  | n/a
25 | ACI to provide updated flows to BSIS | 28/6/16 |  |  | ACI | E | Open |  | n/a
26 | Confirm expected behaviour for initiation of scokets and logon messages between gateway and CI (can members log on/log off) | 28/6/16 | 2016-06-29 |  | ACI/BSIS | E | Closed | BSIS confirmed CI to initiate | n/a
27 | BSIS to clarify requirements for duplicate handling for repeats/retries and cross over transactions | 28/6/16 |  |  | BSIS | E | Open |  | M
28 | SIP to FDP out of scope for certification | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | n/a
29 | Returns/Reversals - No alarms/alerts required | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | n/a
30 | Returns/Reversals will always be responded with an acceptance code | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 28/6 | n/a
31 | For repeats should we send proteo a 9200 or 9201 | 28/6/16 |  |  | BSIS | E | Open |  | S
32 | BSIS need to confirm suspense A/c's and processing | 28/6/16 |  |  | BSIS | E | Open | potentially around 5 suspense a/c's. list of sort code or a/c no would trigger what suspense a/c to use | L
33 | BSIS to confirm behaviour on timeout of outbound return | 28/6/16 |  |  | BSIS/ACI | E | Open | BSIS to discuss and confirm. ACI to add flow to msg flow doc | M
34 | BSIS to confirm that they will do the accounting hold/post processing for payments from the warehousechannel(outbound) | 28/6/16 |  |  | BSIS | E | Open |  | M
35 | BSIS to confirm outbound SOP/FDP will be non-file based | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS agreed in W/shop 29/6 | XL | x
36 | channel outbound to CI approved by host and response fails to get back to channel - ACI to advise what happens in Standard gateway processing (alert/alarm/event?) | 28/6/16 |  |  | ACI | E | Open |  | ?
37 | Timeouts to CI - Can we accumulate number of timeouts and generate alarms - BSIS to confirm to go with standard processing | 28/6/16 | 2016-06-29 |  | ACI/BSIS | E | Closed | ACI confirmed accumulation threshold is configurable | n/a
38 | ACI to confirm that we can forward unsolicited admin messages to proteo | 28/6/16 |  |  | ACI | E | Open |  | S
39 | BSIS to confirm In an unmatched reversal to use the suspense account and not the customer account before forwarding to Proteo | 28/6/16 | 2016-06-29 |  | BSIS | E | Closed | BSIS confirmed one of the 5 suspense account to be used | L
40 | BSIS to confirm flow for SIP to FDP and exception conditions | 28/6/16 |  |  | BSIS/ACI | E | Open | BSIS confirmed to treat as SIP failure. ACI to add to msg flow doc. Will require further discussion | L

## SDD Questionairre
Action Id. | Action | Date Raised | Date Closed | Date Required | Owner | Status | Comments
1 | Server and Operating System - TSB/BSIS Workshop Response : It is expected to be a RHEL Linux Implementation on x86 but this will be confirmed during future workshops | 28/5/16 |  |  | BSIS | Open | 10/5/16 - Redhat Enterprise Linux, Intel x86_64 | close?
2 | Database Server - TSB/BSIS Workshop Response : It is expected that the deployment will be on Oracle, but this is to be confirmed during future workshops | 28/5/16 |  |  | BSIS | Open | 10/5/16 Oracle 12c | close?
3 | Stack Configuration - TSB/BSIS Workshop Response : Expected to be RHEL v7 but this is to be confirmed during future workshops | 28/5/16 |  |  | BSIS | Open | 10/5/2016 - Redhat Enterprise Linux | close?
4 | Hardware Security Modules (HSM) - TSB Workshop Response : Open question to TSB/BSIS to confirm | 28/5/16 |  |  | BSIS | Open | 10/5/16 Thales HSM 8000, payShield 9000 | close?
5 | Database Replication - Distance between Sites | 28/5/16 |  |  | BSIS | Open | 10/5/16 - 6 miles | close?
6 | Retention period for offload database | 28/5/16 |  |  | BSIS | Open | 10/5/16 - 1 year | Close?
7 | Communications Protocol - for connecting the TSB’s Host into the Faster Payment Gateway | 28/5/16 |  |  | BSIS | Open | MQ | close?
8 | Sessions Contracted - TSB to supply number of Sessions and TPS contracted by the TSB with the UK Faster Payments Scheme for SIP/SOP/FDP. | 28/5/16 |  |  | TSB | Open
9 | Payment Validations – HOST - Date Sent Tolerance check will be performed in proteo. Need to confirm other validations required | 28/5/16 |  |  | BSIS | Open
10 | Section 9 and 10 require further discussion | 28/5/16 |  |  | BSIS/TSB/ACI | Open
11 | FPS Hold Exception Decision - not expecting to be doing hold processing but needs to be confirmed | 28/5/16 |  |  | BSIS/TSB/ACI | Open
12 | FPS USM Decision- USM processing was discussed in the workshop. However we need final confirmation of the processing expected here from TSB | 28/5/16 |  |  | BSIS | Open
13
14
15
16